## Setting out 01
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO
PROJECT
CLIENT
CONSULTANT
MAIN CONTRACTOR
CHECKLIST FOR SURVEYING / SETTING OUT
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Check Levels and locations are as per the approved drawing.
2 | Established reference points and bench marks are maintained at all times during construction.
3 | Check plot dimensions are with respect to affection plan.
4 | Check all NOC's obtained from legal authorities.
5 | Any dimensional discrepancies noted in the drawings.
6 | Verify that setting out has been carried out with respect to standard levels & points in accordance with approved demarcation.
7 | Check stakes are set, sufficiently maintained and not disturbed by construction activities.
8 | All existing levels has been measured & recorded.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Excavation 02
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR EXCAVATION
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Check that existing ground level surveyed against benchmark.
2 | Any out standing works to protect /divert existing services, prior to excavation activity.
3 | Designated storage areas provided to stock excavated material
4 | Approval in place to use the excavated material if required.
5 | Excavation has been carried out to the desired level in accordance with the construction drawings
6 | Safety measures taken against embankment failure & erosion
7 | MEP drainage, electrical, etc. checked and completed.
8 | Bottom of excavation is as per the standard requirements and approved by consultant.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Back filling & Compaction 03
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR BACKFILLING AND COMPACTION
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Selected fill materials and method of statement approved by consultant.
2 | Underlying material / layer has been approved by Engineer.
3 | Material has been laid in specific no of layers and thickness.
4 | Water has been applied and mixed prior to compaction to ensure optimum moisture content.
5 | Method of compaction approved by consultant.
6 | Materials compacted and taken samples for laboratary testing .
7 | Test results satisfactory to the specification and approved for subsequent layer to proceed
8 | Final level checked and approved. by consultant
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Anti-termite 04
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO
PROJECT
CLIENT
CONSULTANT
MAIN CONTRACTOR
CHECKLIST FOR ANTI-TERMITE TREATMENT
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All tests & checks carried out prior to this treatment.
2 | Supplier & material have been approved by Authority/Consultant
3 | Applicator has been approved by Authority/Consultant.
4 | Manufacturer's instructions/procedures implemented during application.
5 | Safety precautions are in place for the application.
6 | Approval to proceed further works obtained from the consultant.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## PCC 05
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR BLINDING (PCC)
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Necessary tests have been conducted on the soil surface.
2 | Check that termite proofing has been carried out as per manufacture's instruction.
3 | Check that approved/specified polythene sheet has been laid under blinding.
4 | Check that Polythene sheet layed with overlaps of 100mm
5 | Check that formwork have been installed properly and release agent applied and meets requirement
6 | Check that the formwork has been fixed and secured properly .
7 | Check that the thickness of PCC are as per the requirements.
8 | Check that MEP drainage, electrical, etc. under blinding has been completed as per the drawing/specification
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Sub strc.waterproofing 06
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR SUBSTRUCTURE WATER PROOFING
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Blinding concrete or substructure properly cured prior to bitumen painting.
2 | Material and Applicator have been approved by Authority/Engineer.
3 | Surface area clean and dry to take bitumen paint.
4 | Concrete surface been cleared of edges, hollows to provide a strong bond of bitumen paint.
5 | Bitumen paint laid to all faces of blinding concrete/vertical and horizontal faces of structure.
6 | Bitumen paint laid in required coats as per manufacturer's recommendation to all surface area
7 | All safety precautions are in place for the application.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## RCC footings 07
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR R.C.C. FOOTING
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All materials in accordance to approved material submittals.
2 | PCC cast after achieving required compaction
3 | Waterproofing,if any completed
4 | Formwork installation has been done properly for firmness, supports,grout Leakage and cleanliness.
5 | Reinforcement placed as per drawings & specifications
6 | Dowels for slab columns,stair cases,walls placed as per specs.
7 | Alignment & orientation checked against grids
8 | Cover blocks/spacers placed as per specifications
9 | Chamfers required at edges are as per drawings/specifications
10 | Setbacks with references to demarcation points checked
11 | MEP works completed and clearance obtained
12 | The area has been cleaned and proper access has been made.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## UG tank bottom & wall 08
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR RCC U.G TANKS -(BOTTOM SLAB AND WALL)
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials are approved by the consultant
3 | Depth of the tank is fixed as per the final manhole invert level to achieve the calculated volume and MEP approval obtained for the same.
4 | All supports,jacks,props etc are installed as per specification and consultant approval.
5 | Formwork installation has been done properly for firmness, supports and cleanliness.
6 | Release agent applied to formwork/shuttering
7 | Reinforcement placed as per drawings and specifications
8 | Type of finishes required are checked.
9 | All setting out including concreting level,cover and all dimensions are correct and within the tolerances.
10 | Area has been cleaned and proper access has been made.
11 | Position and alignment of dowel bar and water stopper as per the drawing and manufacture's recommendation.
12 | Necessary sleeves, electrical conduits and other MEP works installed as per the drawing prior to casting and approval of the same has been obtained.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## UG tank top slab 09
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR RCC U.G TANKS (TOP SLAB )
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials are approved by the consultant
3 | All supports,jacks,props etc are installed as per specification and consultant approval.
4 | Formwork installation has been done properly for firmness, supports and cleanliness.
5 | Release agent applied to formwork/shuttering
6 | Reinforcement placed as per drawings and specifications
7 | Openings for manholes considered
8 | Type of finishes required are checked.
9 | All setting out including concreting level,cover and all dimensions are correct and within the tolerances.
10 | Area has been cleaned and proper access has been made.
11 | All required dowels for shafts,parapets,columns are placed.
12 | Necessary sleeves, electrical conduits and other MEP works installed as per the drawing prior to casting and approval of the same has been obtained.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Tie beam 10
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR R.C.C. TIE BEAM / PEDESTAL COLUMN
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials are approved by the consultant
3 | Masonry solid blocks for the periphery are complete.
4 | Top of tie beam level established and cross checked.
5 | Necessary gate level achieved.
6 | Form work checked for alignment,depth,width and supports.
7 | Release agent applied
8 | Reinforcement placed as per drawings & specifications
9 | Floating columns and main columns,walls,stair cases etc,reinforcement placed as per drawings & specifications.
10 | Necessary sleeves, electrical conduits and other MEP works installed as per the drawing prior to casting and approval of the same has been obtained.
11 | Inspection from survey department if any.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Fill&compaction of subgrade 11
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR FILL AND COMPACTION OF SUB GRADE LEVEL
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Selected fill materials and method of statement approved by consultant.
2 | Sub-structure protection carried out and approved by consultant.
3 | Water proofing has been carried out as per specification and approval.
4 | Approval to proceed further works obtained from the consultant.
5 | Back filling is done in specified no.of layers and in specified thickness.
6 | Method of compaction as approved by consultant,and test results recorded.
7 | Final level checked and recorded.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Blinding-Grade slab 12
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR BLINDING(PCC)-GRADE SLAB
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Levels checked and recorded.
2 | Compaction of ground/formation and test passed.
3 | Termite proofing has been carried out as per manufacture's instruction.
4 | Approved/specified polythene sheet been laid above the treated area.
5 | Formwork has been fixed and secured properly .
6 | Necessary sleeves, electrical conduits and other MEP works installed as per the drawing prior to casting and approval of the same has been obtained.
7 | Thickness of PCC are as per the requirement.
8 | Type of finish required is agreed on/approved.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## RCC Grade slab 13
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR R.C.C.GRADE SLAB
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Levels checked and recorded.
2 | Compaction of ground/formation and test passed.
3 | Blindings,bitumen impregnated fibre board etc…completed as specified & approved
4 | Termite proofing has been carried out as per manufacture's instruction.
5 | Approved/specified polythene sheet been laid above the treated area.
6 | Construction/expansion joints in the slab are as per drawing/method statement and approved by consultant.
7 | Formwork has been fixed and secured properly .
8 | Reinforcement placed as per drawings/specs and proper cover.
9 | Necessary MEP works completed and approval obtained.
10 | Starter bars if any are checked as per drawings.
11 | Thickness of slab(haunching),if any,for partition wall completed.
12 | Type of finish required is agreed on/approved.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Column 14
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR RCC COLUMN
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Layout,mentioning size,shape,height of casting and spacing of columns prepared
2 | Special formwork,if any,in the columns provided.
3 | Approval of MEP works,if any,in the columns taken
4 | Reinforcement placed as per drawings/specifications
5 | Tie rods,if any,fixed to consultant's approval
6 | Approval for reinforcement prior to closing of formwork
7 | Formwork checked for firmness,plumb and supports
8 | Cover to reinforcement is satisfactory,spacer blocks adequately placed.
9 | Starter bars are cleaned and overlap satisfactory
10 | Laitance at construction joints removed and joint cleaned
11
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## RCC wall 15
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR RCC WALL
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | Reinforcement placed as per drawings and specifications
2 | existing concrete surface has been scabbled and joints have been prepared properly.
3 | Formwork checked for grout leakages,dimensions,alignment and proper support with respect to approved drawings.
4 | All openings for inlets & outlets checked as per drawings.
5 | Verticality of the formwork checked and within tolerance
6 | Construction joints are well prepared/no laitance
7 | Starter bars from footing/slab/walls are cleaned
8 | cover blocks/spacers placed adequately and firm
9 | The kicker location checked before closing forms
10 | Necessary sleeves, electrical conduits and other MEP works installed as per the drawing prior to casting and approval of the same has been obtained.
11
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## RCC slab 16
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR R.C.C SLABS AND BEAMS CONSTRUCTION
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials are approved by the consultant
3 | All supports,jacks,props,and cross braces fixed are as per specs & to the consultant's approval.
4 | Floor levels checked and maintained as in drawings
5 | Shuttering/formwork properly checked for alignment and firmness
6 | All the necessary ducts openings,concrete stops considered
7 | Release agent applied to formwork/shuttering
8 | Reinforcement placed as per drawings and specifications.
9 | All required dowels for shafts,paapets,columns etc…are placed.
10 | Necessary sleeves, electrical conduits and other MEP works installed as per the drawing prior to casting and approval of the same has been obtained.
11 | Shuttering/formwork sufficiently wet prior to casting.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Block work 17
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR BLOCK WORK
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials are approved by the consultant
3 | Required tests are conducted to specified frequency
4 | Layout prepared considering all the joints and openings
5 | Insulation,reinforcement,accessories are in place
6 | Mortar mixed as specified
7 | Blocks wet before placing
8 | Each course checked for alignment and verticality
9 | Number of courses as specified
10 | All joints properly filled and pointed/flush as specified
11 | Wall anchorages checked (where required)
12 | Necessary ducts(MEP & Electrical), opening is provided and approved.
13 | Openings for doors and windows are set plumb and true
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Plastering 18
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR PLASTERING WORK
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials and fixtures approved by the consultant
3 | Preliminary MEP works complete
4 | Plaster accessories are fixed to consultant approval
5 | Concrete surfaces are roughned/approved coating sprayed prior to plastering
6 | Block works applied with scratch coat at least 24 hours prior to plastering
7 | Level pads fixed,considering the specified minimum thickness of plaster
8 | Mortar homogenously mixed by mechanical mixers or as agreed with consultant
9 | All timber frames and steel frames fixed prior to plaster
10 | Surfaces wet prior to plaster
11 | Surfaces roughened where tiles are applicable
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Roof waterproofing 19
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR ROOF WATER PROOFING
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials and Method statement approved by the consultant
3 | Preliminary MEP works complete
4 | Roof is cleaned and all loose materials removed
5 | Primer laid to approval
6 | Liquid membrane/sheeting/combo system laid to manufacturer instruction
7 | Laps,fillets and flashing checked
8 | Flood test complete to approval,procedure and result recorded
9 | All necessary guarantees recorded
10 | Necessary approvals taken prior to commencing of tile workes or other protective works
11
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Painting works 20
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR PAINTING (CONCRETE/PLASTER SURFACE) WORKS
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials and Method statement approved by the consultant
Surface Preparation
3 | Fresh surface cured for 21 days (applicable to new coating only)
4 | Moisture level as per manufacturer's recommendations
5 | Surface free from algae,unstable matters,grease or oil
6 | Surface cleaned/scrubed to receive primer coats
7 | Substrate hairline cracks patched
Paint Preparation
8 | Name,color and type of paint inspected and conform to specifications
9 | Thinning ratio and mix ratio in accordance to manufacturer's recommendations
10 | Paint used is within pot life
Painting Environment
11 | Adequate ventilation and lighting provided
12 | Surrounding temperature and relative humidity is checked to manufacturer's recommendations.
Paint Application
13 | No. of coats and location of application checked
14 | Parts not to be painted protected prior to commencement of work
15 | Painting frequency,interval and wet film thickness to manufacturer's recommendations
16 | Drying time is checked
17 | Color,gloss and texture (if required) checked as per approved sample
18 | Completed painting work protected
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Ceramic tiles 21
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR CERAMIC TILES
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials and Method statements approved by the consultant
3 | Layout of tiling prepared or as agreed with client/consultant
Floor
4 | MEP works completed and clearence obtained from the concerned department.
5 | Water proofing checked and approved
6 | Surface is free of oil
7 | Datum points are established under the supervision of site engineer
8 | All anchors,inserts are installed prior to tiling
9 | Tiles are immersed in water prior to placing
10 | Spacers are used to assure uniform spacing between tiles
Wall
11 | Mortar/glue consumed before initial set
12 | Mortar/glue is applied properly to avoid any hollowness beneath
13 | Grout lines of wall tile match with that of floor tiles or as agreed with client/consultant
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## False ceiling 22
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR FALSE CEILING
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials and Method statements are approved by the consultant
3 | All MEP services are installed and checked
4 | Positioning of service outlets in grid is completed
5 | Line and levels of installed grid checked
6 | Hangers are fixed and completed as per the requirements.
7 | Alignment of ceiling tiles completed and approved.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Marble-Granite 23
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR MARBLE/GRANITE WORK
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials and Method statement approved by the consultant
3 | All concerned MEP works are complete
Flooring
4 | Levels/Datum established
5 | Workface of tiles,pattern etc.considered
6 | Compact mortar ensured below the tiles
7 | Mortar consumed before initial set
8 | Grouting if any,completed to approvals
9 | protection of tiles against damage ensured.
Cladding
10 | Line,level and verticality checked and established
11 | Approved metal clamps are securely fixed in position
12 | Work face and patterns as specified
13 | Protective coat (if any) applied
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Aluminium work 24
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR ALUMINUM/WOODEN WORKS
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials and samples are approved by the consultant
3 | All the openings for doors & windows are as per the measurement forwarded for fabrication.
4 | All units received from the workshop have "QC passed" tag
5 | Plaster work completed and approved
6 | All gaps are properly sealed
7 | Drainage (if applicable) is provided for bottom members
8 | All the fittings are in good conditions
9 | Testing if any completed and approved
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Curtain wall 25
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR CURTAIN WALL
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials and samples are approved by the consultant
3 | Surface is clean and bitumen paint is applied wherever applicable
4 | Position of anchor bolt as in the shop drawing.
5 | Torque for the anchor bolt.
6 | The line of transoms/mullions compatible with civil works.
7 | Transoms pins are properly fastened to the mullion
8 | PVC packing inserted between brackets & Mullion.
9 | Water proofing tape fixed prior to external finishes.
10 | Places where gasket is cut to receive glass holders, is sealed with sealant.
11 | Pressure plates have sufficient drainage & air passage holes.
12 | Pressure plate / cover plate joints are not overlapping with mullion joints.
13 | Water pressure test & Torque test completed & approved. Results are recorded.
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….

## Interlocking tiles 26
The Client |  |  | The Project Management / The Consultant |  | The Contractor
JOB.NO |  | 0
PROJECT |  | 0
CLIENT |  | 0
CONSULTANT |  | 0
MAIN CONTRACTOR |  | 0
CHECKLIST FOR INTERLOCKING TILES & KERBSTONE
LOCATION : Date:
REFERENCES(DRAWING,SPECIFICATION,PROCEDURE) :
CL NO.:
Sl.no | ATTRIBUTE |  |  |  |  | YES | NO | N/A
1 | All the materials comply with the project specifications
2 | All the materials and samples are approved by the consultant
3 | Datum fixed and approved by Consultant.
4 | Required level achieved by excavation/backfill are approved and recorded.
5 | All services including Manholes, Electrical, Plumbing & Drainage, etc. completed or brought up to the required level.
6 | Type,position and levels of Kerbstones are as per the shop drawing.
7 | Sub strata compacted by road base are approved and tested.
8 | Level & alignment of Kerbstone checked and approved by the Consultant.
9 | Pattern of interlock approved
REMARKS:
Checked by:
Civil Works:
Name: |  | Position: |  | Signature: |  |  | Date:
MEP Works
Name: |  | Position: |  | Signature: |  |  | Date:
QC Signature:……………………… | [5 empty] | Date:………………….