## Back fill
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  |  |  | LEGENDS:
PROJECT |  |  |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  |  |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  |  |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
4 | BACKFILL& COMPACTION UPTO SUBGRADE LEVEL (BELOW FOOTING AND GRADE SLAB) | a) Check all drawings for latest revision and approval. |  |  |  |  | C1 | R
b) Check and ensure that all delivered materials
|  | conform to contract specifications. |  |  |  |  | C1 | M
c) Check that method statements submitted and
|  | approved. |  |  |  |  | C | R
d) Check that founding level is tested for Insitu Density,
for footing and below grade slab.(Soil and Road Base)
|  | Soil-95%,Road base-98% | Contract Drawing,Specification | Approved Drawing, Inspection Request, Q.C Check list, Field Density Report |  |  | C1 | I
|  | e) Check that sub grade is smooth and conforms to the |  | Method statement
alignment, grade and cross-section shown on the
plans and as required by the project construction
|  | specification. |  |  |  |  | C1 | I
f) Ensure that the relevant tests for (formation and
roadbase) were carried out and samples were taken
|  | as per the specification. |  |  |  | SC1 | M | M
|  | g) Final Inspection |  |  |  |  | C1 | M