## BLOCK WORK
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  |  |  | LEGENDS:
PROJECT |  |  |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  |  |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  |  |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
10 | BLOCK WORK
a) Ensure that Material,Shop drawings/Method statements
|  | are approved and at correct revision. |  |  |  |  | C1 | R
|  | b) Ensure that mortar mix in use as per the approval |  |  |  |  | C1 | M
of consultant.
|  | c) Ensure that block in use manufactured, |  | Approved Drawing, Approved Materials, Certificate Of Compliance, Inspection request, And QC Check List | Forman, Site Engineer, Project Engineer And QC Engineer |  | C1 | M
|  | supplied and tested in accordance with | Specification for Blockworks, Approved Drawings, Project Quality Plan, Method Statement
the requirements.
d) Ensure that block work properly levelled
|  | and plumbed. |  |  |  |  | C1 | I
e) Ensure that curing is carried out as per the
|  | requirements. |  |  |  |  | C1 | M
|  | f) Anchors,ties,inserts,plugs are placed in position as per consultant approval |  |  |  |  | C1 | M
|  | g) Ensure that spaces around the door and window frames are filled solidly with mortar. |  |  |  |  | C1 | M