## concrete (PCC)
ITP REF :
DATE :
PAGES : 1 OF 2
INSPECTION AND TEST PLAN
PROJECT NO |  |  |  | LEGENDS:
PROJECT |  |  |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  |  |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  |  |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
6 | CONCRETE :
A) BLINDING (P.C.C)
| 1) PREPOUR | a) Ensure that Shop drawings/Method statements are
|  | approved. |  |  |  |  | C1 | M
|  | b) Check all formwork stability,support,alignment | Project Quality Plan, Specification for Concrete works, Method Statement | Approved Drawing, Material Apprval, Inspection Request, Q.C Check list, FDT result | Forman
|  | and dimension. |  |  | Project Engineer |  | C1 | M
QA/QC Engineer
|  | c) Ensure that base soil compaction test are done. |  |  |  |  | C1 | H
|  | d)Ensure that site inspection certificate confirming the bearing pressure and depth of foundation is obtained from the laboratory. |  |  |  |  | C1 | M
|  | e) Ensure that 1000 gauge polythene sheet is laid. |  |  |  |  | C1 | M
2) PLACEMENT
|  | a) Ensure that Concrete is in accordance with approved |  | Delivery Note | Forman |  | C1 | H
|  | design mix. | Specification for Concrete works, Project Quality Plan, Method Statement | Inspection Request | Project Engineer
|  |  |  | Q.C Check list | QA/QC Engineer
|  | b) Inspect placement of concrete. |  |  |  |  | C1 | M
|  | c) Protect as necessary. |  |  |  |  | C1 | M
|  | d) Check all required prepour test of the concrete i.e.temperature,slump etc.are in place. |  |  |  |  | C1 | M
6 | 3) POST POUR | a) Check Curing in accordance with approved
|  | specification. |  |  |  |  | C1 | M
|  | b) Check finishes in accordance with specification. |  |  |  |  | C1 | M
|  | c) Check surface repair(If any) has been carried out, in | Specification | Inspection Request | Project Engineer
|  | accordance with approved repair procedure. | for Concrete | Q.C Check list | QA/QC Engineer |  | C1 | M
Test result
Method Statement
|  | d) Check the surface finishes. |  |  |  |  | C1 | M
|  | e) Final inspection/document review. |  |  |  |  | C1 | M
"Type equation here."