## Concrete Substructure
ITP REF :
DATE :
PAGES : 2 OF 2
INSPECTION AND TEST PLAN
PROJECT NO |  | : J#8287 |  | LEGENDS:
PROJECT |  | : Proposed Warehouse (G+M) |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  | : M/s Shree Traders |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  | : M/s.New Arch Engineering Consultant |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
7 | CONCRETE
R.C.C SUBSTRUCTURE
| (FOOTING,TIE BEAM, | a) Ensure that drawings are approved and at correct
|  | revision. |  |  |  |  | C1 | R
PEDESTAL)
| 1) PREPOUR | b) Ensure that material approval (rebar, concrete mix)
|  | are in place. |  |  |  |  | C1 | R
|  |  | Project Quality Plan, Specification for Concrete Works, Approved Drawing. | Inspection Request, Q.C Check list, FDT result, MEP clearance form | Forman, Site Engineer/Project Engineer & QA-QC Engineer.
|  | c) Check all formwork is in accordance with specification |  |  |  |  | C1 | M
d) Check all embedded items and reinforcement are in
|  | accordance with specifications. |  |  |  |  | C1 | M
|  | e) Ensure that MEP Clearence obtained |  |  |  |  | C1 | R
f) Check the area is cleaned and proper access has
|  | provided. |  |  |  |  | C1 | M
|  | g)Ensure that the required authority approval is obtained |  |  |  |  | C1 | H
2) PLACEMENT
a) Ensure that Concrete is in accordance with approved
|  | design mix. |  |  |  |  | C1 | M
Inspection request, QC Check List, Test Result, Delivery Note.
|  | b) Perform and record all required tests such as; | Specification for Concrete Works, Method Statement, Approved Drawing. |  | Forman, Site Engineer/Project Engineer & QA-QC Engineer.
compressive strength, slump test,air content
|  | temperature test etc. |  |  |  |  | C1 | M
|  | c) Inspect placement of concrete. |  |  |  |  | C1 | M
|  | d) Protect as necessary. |  |  |  |  | C1 | M
7 | 3) POST POUR | a) Check Curing in accordance with approved
|  | specification. |  |  |  |  | C1 | M
|  | b)Check Finishes in accordance with specification. |  |  |  |  | C1 | M
c) check surface repair(If any) has been carried out, in
|  | accordance with approved repair procedure. | Method Statement, General Specification for Concrete Works | Inspection Request |  |  | C1 | M
|  |  |  | Q.C Check list | Project Engineer
|  |  |  | Test result | QA/QC Engineer
d) check the surface finishes after repairing.
[7 empty] | C1 | I
[7 empty] | C1 | M
e) Check provision of waterproofing.
|  | f) Final inspection/document review. |  |  |  |  | C1 | M