## doors windows
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  |  |  | LEGENDS:
PROJECT |  |  |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  |  |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  |  |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
12 | INSTALLATION OF
| DOORS,WINDOWS | a) Ensure that Drawings are approved and are
| AND HARD WARES | at correct revision. |  |  |  |  | C1 | R
(INCLUDES ALUMINIUM AND WOODEN)
b) Ensure that all material and subcontractors approval
|  | are in place. |  |  |  |  | C1 | R
c) Ensure that Section and colour are as
|  | per the approval obtained |  |  |  |  | C1 | R
|  | d) Ensure that all the installation are as per the | Approved Drawing, Contract Specification, Finishes Schedule
|  | approved drawings. |  | Inspection Request, QC Check List |  |  | C1 | M
e) Ensure that all the accessories and glazing work
|  | are as per the specification and drawings. |  |  | Foreman & Site Engineer |  | C1 | M
Project Engineer
|  | f) Ensure that all the decoratives finishes as per the |  |  | QA/QC Engineer
|  | approved finishes schedule. |  |  |  |  | C1 | I
I