## Excavation
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  |  |  | LEGENDS:
PROJECT |  |  |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  |  |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  |  |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
3 | EXCAVATION
|  | a) Ensure that DM Building permit have been obtained prior to construction commencement. |  |  |  |  | C1 | M
|  | b)Check Drawings are approved & at correct revision |  |  |  |  | C1 | R
c) Survey and mark out all excavations prior to
|  | commencement of work. |  |  |  |  | C1 | M
|  | d)Trial pits are conducted to make sure that excavation area free from existing services. |  |  |  |  | C1 | S
e) Verify the existing utilities have been indentified,
|  | relocated /protected as necessary. |  |  |  |  | C1 | R
Standard specification & General
|  | f) Ensure all grades and elevations are set in | Conditions from Water & Power
|  | accordance with relevant drawings and survey | Authority
|  | requirements. |  |  |  |  | C1 | M
|  |  | Contract Specification |  | Project Engineer
|  | g) Ensure that all excavation works, whether by machine | Approved drawings |  | QA/QC Engineer
|  | or by hand, are performed in a safe working manner. | Approved drawings | Approved Drawing, Inspection Request, Q.C Check list | Surveyor |  | C1 | M
|  | h) Ensure that all dewatering systems are in place and |  | Method statement
|  | in good working condition.(if required) |  | Soil Investigation report |  | SC1 | M | M
i) Visually check that bottom of excavations are free
from extraneous materials, ground water, and ready
|  | for Roadbase/PCC works. |  |  |  |  | C1 | I
j) Ensure that FDT/Proctor test has been done as per
|  | the requirement |  |  |  | SC1 | M | M
k) Identify remove and dispose of all
|  | unsuitable materials to designated site. |  |  |  |  | C1 | M