## EXTERNAL WORK
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  | : J#8287 |  | LEGENDS:
PROJECT |  | : Proposed Warehouse (G+M) |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  | : M/s Shree Traders |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  | : M/s.New Arch Engineering Consultant |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
17 | EXTERNAL WORKS( Kerbstone and Interlock)
|  | a) Ensure that Material,Shop drawings/Method statements are approved and at correct revision. |  |  |  |  | C1 | R
|  | b) Ensure that material delivery is as per the dimension, Compressive strenght etc. |  |  |  |  | C1 | R
|  | c) Ensure that block in use manufactured, supplied and tested in accordance with the requirements. | Specification for Paving Works, Approved Drawing, Project Quality Plan, Method Statement. | Approved Drawings, Approved Materials, Certificate of Compliance, Inspection Request, Check List | Site Engineer, Project Engineer, QA/QC Engineer | SC | R | R
|  | d) Ensure that paving work properly levelled and aligned. |  |  |  |  | C1 | I
|  | e) Ensure that interlocking tiles are laid according to the approved patterns. |  |  |  |  | C1 | M
|  | f) Ensure that MEP Clearence obtained |  |  |  |  | C1 | M