## MEP
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  | : J#8287 |  | LEGENDS:
PROJECT |  | : Proposed Warehouse (G+M) |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  | : M/s Shree Traders |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  | : M/s.New Arch Engineering Consultant |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
16 | MEP WORKS
|  | a) Shop drawings/Method statements are approved | Method of statements | Approved drawings,
|  | and at correct revision. | drawings | Method of statements |  |  | C1 | R
|  | b) Ensure that the material submittal is approved | Material submittals | Approved Material Submittal |  |  | C1 | R
Mechanical Engineer, Electrical Engineer, MEP Incharge
|  | c )Ensure that all MEP Works |  | MEP Clearance Form
|  | are as per the specification and drawings | MEP Specification | Inspection Request |  |  | C1 | I