## Mobilization
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  | : |  | LEGENDS:
PROJECT |  |  |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  |  |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  |  |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
1 | Mobilization
|  | a) Check that B.P & approved drawings are received and at its latest revision. |  |  |  |  | C1 | M
|  | b) Ensure that the Demarcation & level certificate obtained from the authority. |  |  |  |  | C1 | M
|  | c) Ensure that Fencing approval & car parking permission obtained from the permits department. |  |  |  |  | C1 | M
Coordination Drawing
|  | d) Check/fix approved type of fencing or protection barricades are | Project Quality Plan | Demarcation Certificate | Foreman Surveyor Project/Site Engineer QA/QC Engineer Safety Office |  | C1 | S
|  | within or allowable limits of the proposed project. | General Specification | Inspection Request
|  |  | Approved Drawings | Check List
|  | e) Ensure that all necessary/important documents i.e.NOC's,Permits and licenses are available at the site for checking at all times. |  |  |  |  | C1 | I,M
|  | f) Ensure that the working area to be levelled and cleared from any materials that might disrupt or impede the activities during its execution. |  |  |  |  | C1 | M
|  | g) Ensure that all temporary site facilities,including signs/billboards be installed and provided as per the approved site plan. |  |  |  |  | C1 | M