## PAINTING
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  |  |  | LEGENDS:
PROJECT |  |  |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  |  |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  |  |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
14 | PAINTING
|  | a).Ensure that the method statement is approved. |  |  |  |  | C1 | R
|  | b).Ensure that the material submittal is approved. |  |  |  |  | C1 | R
|  | c).Handling and Storage of materials are in accordance with relevant specifications. |  |  |  |  | C1 | M
d).Ensure that the surface is free of oil.
[7 empty] | C1 | M
|  | e).Ensure that only qualified applicators will perform the Job. |  |  |  |  | C1 | M
Project Quality Plan, Material Submittal, Method Statement, Specification and Schedule of Finishes
|  | f).Humidity, weather, air and surface temperature check have been performed, recorded and approved. |  | Approved Submittals, Inspection Request, and QC Check List. | Forman, Site Engineer, Project Engineer and QA/QC Engineer. |  | C1 | R
|  | g).Degree of cleanliness and surface profile are in accordance with the specification. |  |  |  |  | C1 | M
|  | h).Check the application and finishing are as per the approved method statement and as per Manufacture's recommendation. |  |  |  |  | C1 | M
|  | i).Final inspection and approval for the finished surface |  |  |  |  | C1 | I