## PLASTERING
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  |  |  | LEGENDS:
PROJECT |  |  |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  |  |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  |  |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
13 | PLASTERING
|  | a).Ensure that method statement is approved. |  |  |  |  | C1 | R
|  | b). Ensure that material submittal is approved. |  |  |  |  | C1 | R
c).Check the surface of concrete wall and block work
prior to application of plaster for its cleanliness,
|  | sound conrete, installation of level markers etc. |  |  |  |  | C1 | M
|  | Note: Major repairs if any to be carried out as per | Specification & Method of Statement, Project Quality Plan & Approved Drawing. |  | Forman, Site Engineer, Project Engineer an QA/QC Engineer
|  | separate method statements. |  | Approved Drawing, Inspection request and Check List
d). Check the plastering accessories deliverd and in use
|  | are as per the approval. |  |  |  |  | C1 | M
e). Check the application and finishing are as per the
|  | approved method statement. |  |  |  |  | C1 | M
f). Check the curing is carried out as per the approved
|  | method statement. |  |  |  |  | C1 | M
g). Final inspection and approval for the finished surface
|  | prior to any surface treatment. |  |  |  |  | C1 | I