## STEEL ERECTION WORKS
ITP REF :
DATE :
PAGES : 1 OF 1
INSPECTION AND TEST PLAN
PROJECT NO |  |  |  | LEGENDS:
PROJECT |  |  |  | I= Inspection | H=Hold | SC=Sub-Contractor
CLIENT |  |  |  | W =Witness | M= Monitor | C=Contractor
CONSULTANT |  |  |  | R =Review Records | C1=Contractor Mandatory | E/A=Engineer/Authority
DISCIPLINE |  | : CIVIL |  | S =Surveillance | SC1= Sub Contractor mandatory
SL.NO | ACTIVITY | INSPECTION/TEST METHOD | SPECIFICATION/DRAWING REFERENCE | VERIFYING DOCUMENTS/ACCEPTANCE CRITERIA | RESPONSIBLE PERSON AT LOCATION | RESPONSIBILITY
[6 empty] | SC | C | E/A
11 | STEEL ERECTION
a) Ensure that Erection drawings/Method statements are
|  | approved and at correct revision. |  |  |  |  | C1 | R
|  | b) Ensure that Erection material as per |  |  | Project Engineer, Erection Engineer or Erection In-charge, QA/QC Engineer.
|  | the contract and specification | Contract drawings | Method Statement, Inspection Request. |  |  | C1 | R
Contract Specification
QA/QC check list
c)Ensure that all materials and installations
|  | are as per the specification and drawings. |  |  |  |  | C1 | I