## Weekly Monitor Report
The Client |  |  | The Consultant | [8 empty] | The Contractor
Job No: |  |  | WEEKLY MONITOR REPORT # (Report no.) | [8 empty] | 1-Internal Recovery Bar Chart # (No.)
Consultant Recovery Bar Chart: | [11 empty] | Completion Date Targeted - / /
Dated: / / - Completion Date: / / |  |  |  | Date: From / / to / /
Planned Time Schedule | [5 empty] | Accomplished Work
Act. ID | Activity Description | Planned Duration | Early Start Date | Early Finish Date | Planned Total Quantity (A) | Actual Duration | Actual Start Date | Actual Finish Date | Total Accomplished Quantity |  |  | Accomp. Work % (B/A) | Remarks / Reasons of Delay
[9 empty] | Previous | Quantity / Week | Total (B)
| Planning Engineer |  |  |  |  | QA/QC Engineer | [6 empty] | Project Manager

## guide
Weekly Monitor Report
1- | Before starting to use this form , the Planning Engineer should prepare internal actual and applicable time schedule accepted and signed from Project Manager,MEP Manager and approved from the Director, and send copies for all conern departments.
2- | This program will be obligated to all related departments and subcontractors.
3- | The program will be updated if need to be applicable until project hand over.
4- | The project manager will prepare weekly monitor report at the end of every week and forward to the Operations Manager, the report will be discussed in the head office during the weekly meeting,
5 | The form contain comparison between the planned time schedule and the actual work done in the site during the week.
6- | The data to be included in the report are as follows:-
6.1 | From Planned Time Schedule :-
a- | Activity ID
b- | Activity Description
c- | Planned Duration
d- | Early start and Early finish
e | Planned total quantity either from op52 considering any variations or the exact quantities if available
6.2 | From Weekly Accomplishment Work in site :-
a- | Actual Duration
b- | Actual start and Actual finish
c- | Quantities (previous if any, week work done and cumulative quantity)
6.3 | Accomplishment work percent
Shown the total work done up to report date relative to the total quantity.
6.4 | Remarks/Reasons of Delay