Document 2. Resource support for the “Language College 4.0” model

Prepared by: PE “Language College Priority”, Chernivtsi, Ukraine

Date: April 26, 2026

Purpose: Technical description of needs for launching a pilot regional language hub within the implementation of the Seoul Declaration

# I. Concept and target purpose of the model

The “Language College 4.0” model is a hybrid educational ecosystem that combines:

- live learning in classrooms in Chernivtsi;

- distance learning for learners from remote regions, people with disabilities and foreign students;

- engagement of native speakers and teachers from abroad through online platforms;

- elements of robotics and AI for automating routine tasks.

Target languages: English, German, French, Spanish, Korean, Ukrainian (for foreigners).

Target audiences: preschool children, schoolchildren, students, specialists (medical workers, engineers, production specialists, cultural professionals), people with disabilities, residents of remote communities, foreign students.

# II. List of required equipment

1. Basic hardware for distance and hybrid learning:

- Interactive panels (75–86” diagonal) — 3 pcs.

- Laptops for teachers (RAM 16+ GB, SSD 512 GB, Full HD webcam) — 10 pcs.

- Tablets for students (10”, with keyboard) — 15 pcs.

- PTZ cameras with autofocus and tracking — 3 pcs.

- Lavalier microphones and conference system — 5 sets.

- Server or cloud infrastructure (rental) — 1 server / cloud plan.

- Voltage stabilizers and uninterruptible power supplies — 5 pcs.

- Wi-Fi routers (Mesh system) — 3 pcs.

2. Specialized equipment for inclusive learning:

- Braille displays.

- Specialized keyboards (high-contrast, enlarged).

- FM systems (hearing transmitters).

- Adjustable tables for wheelchairs.

- Screen access software (licenses).

3. Equipment for VR/AR learning (prospective component):

- VR headsets (standalone) — 3 pcs.

- Licenses for a VR platform for language learning.

# III. Software and platforms

1. Platform core — LMS (Learning Management System).

Requirements for the LMS platform:

- Support for synchronous (videoconferencing) and asynchronous (recorded courses) learning.

- Built-in test builder and automatic checking.

- Compatibility with screen readers and real-time subtitling.

- API integration with external services (Zoom/Google Meet, payment systems, chatbots).

- Multilingual interface (Ukrainian, English, Korean).

- Protection of personal data in accordance with GDPR.

Recommended solutions: Moodle (free core) or commercial analogues (Canvas, TalentLMS).

2. Platform for videoconferencing and live classes:

- Zoom Education / Google Meet Enterprise.

- Integration with LMS for automatic recording and archive storage.

3. Specialized software for language learning:

- Interactive trainers (Rosetta Stone, Babbel for Business, Talkpal AI, own adaptive developments).

- Platforms for speaking practice (Italki, own service with teachers from Korea).

- AI assistants (Grammarly, LanguageTool, ChatGPT Edu, specialized language AI).

4. Components for inclusive learning:

- Automatic subtitling service (for example, Otter.ai, Whisper integration).

- Audio description of video materials.

- Support for the WCAG 2.1 protocol for all digital resources.

# IV. Educational and methodological support

1. List of required educational materials:

English:

- Textbooks for levels A1–C2 (Outcomes, English File series).

- Materials for preparation for IELTS, TOEFL, Cambridge Exams.

- Professional modules: English for Medical Purposes, English for Engineering, English for Manufacturing.

Languages of EU countries (German, French, Spanish):

- Textbooks for levels A1–B2 (Schritte International, Édito, Aula Internacional series).

- Materials for preparation for TestDaF, DELF/DALF, DELE.

Korean:

- Textbooks for levels A1–B2 (Sejong Korean, Integrated Korean).

- Materials for preparation for TOPIK I and II.

- Specialized modules: Korean for Business, Korean for Technology.

Ukrainian for foreigners:

- Textbooks “Yabluko”, “1000 Ukrainian Words”, Ukrainian for Foreigners.

- Audio and video courses for cultural adaptation.

Children’s programs (preschool and school age):

- Storytelling materials, game sets, songs, multimedia courses.

2. Digital content:

- Recorded video lessons (studio quality).

- Interactive exercises and tests with automatic checking.

- Database of simulation dialogues for professional fields (medicine, manufacturing, culture).

- VR scenarios (prospective content).

# V. Human resources

- English language teachers — 4 (in-person and remote work).

- German / French / Spanish teachers — 3 (combination possible).

- Korean language teacher (native speaker) — 1 (remotely, preferably from Korea).

- Ukrainian language teacher for foreigners — 1 (in-person and remote).

- Methodologist-content developer — 1.

- Technical LMS administrator — 1.

- Tutor for inclusive groups — 1.

# VI. Premises and infrastructure

- 3 equipped classrooms for hybrid learning.

- 1 coworking area for independent student work with tablets.

- 1 sound recording / video recording studio for content creation.

- Area for VR classes (prospective).

- Ensuring physical accessibility (ramps, wide doorways, absence of thresholds).

# VII. Launch stages

Stage 1 — Pilot launch (6 months):

- Basic equipment for hybrid learning.

- LMS setup and integration of videoconferencing.

- Purchase of software licenses for subtitling and screen readers.

- Development of the first online courses (English, Ukrainian for foreigners).

- Engagement of a Korean language teacher (remotely).

Stage 2 — Expansion (12 months):

- Launch of the full range of languages.

- Implementation of the inclusive direction.

- Purchase of VR sets and development of the first scenarios.

- Start of exchange and internship programs.

Stage 3 — Scaling (24 months):

- Operation as a regional hub for the Smart Villages of Bukovyna.

- Creation of a franchise or partner network in other regions.

# VIII. Estimated budget

All amounts are provided in Ukrainian hryvnias (₴) and in US dollars ($) at the approximate exchange rate of 42 UAH/$.

Stage 1 — Pilot launch (6 months):

Equipment:

- Interactive panels (3 pcs. × 100,000 ₴) — 300,000 ₴ (~$7,150)

- Laptops (10 pcs. × 35,000 ₴) — 350,000 ₴ (~$8,300)

- Tablets (15 pcs. × 11,000 ₴) — 165,000 ₴ (~$3,900)

- PTZ cameras (3 pcs. × 25,000 ₴) — 75,000 ₴ (~$1,800)

- Microphones and conference system (5 sets × 5,000 ₴) — 25,000 ₴ (~$600)

- Wi-Fi routers (3 pcs. × 5,000 ₴) — 15,000 ₴ (~$360)

- Voltage stabilizers and UPS (5 pcs. × 4,000 ₴) — 20,000 ₴ (~$480)

- Specialized equipment for inclusion — 105,000 ₴ (~$2,500)

Software:

- LMS setup and customization — 60,000 ₴ (~$1,430)

- Zoom Education / Google Meet licenses (6 months) — 40,000 ₴ (~$950)

- Screen reader licenses and basic subtitling software — 25,000 ₴ (~$600)

- AI assistants (6 months) — 30,000 ₴ (~$710)

Educational materials:

- Purchase of textbooks — 80,000 ₴ (~$1,900)

- Development of the first online courses — 70,000 ₴ (~$1,670)

Personnel (6 months):

- Payroll fund — 1,314,000 ₴ (~$31,290)

Premises:

- Rent of 3 classrooms, coworking area and studio (6 months) — 120,000 ₴ (~$2,850)

- Utilities, internet (6 months) — 60,000 ₴ (~$1,430)

- Accessibility adaptation (ramps, doors) — 50,000 ₴ (~$1,190)

Contingency expenses (10%) — ~287,000 ₴ (~$6,830)

Total Stage 1: ≈ 3,156,000 ₴ (~$75,150)

Detailed payroll fund (6 months):

- English teachers (4 × 20,000 ₴ × 6) — 480,000 ₴

- European language teachers (3 × 18,000 ₴ × 6) — 324,000 ₴

- Korean language teacher (1 × 15,000 ₴ × 6) — 90,000 ₴

- Ukrainian teacher (for foreigners) (1 × 15,000 ₴ × 6) — 90,000 ₴

- Methodologist-content developer (1 × 22,000 ₴ × 6) — 132,000 ₴

- Technical LMS administrator (1 × 18,000 ₴ × 6) — 108,000 ₴

- Tutor for inclusive groups (1 × 15,000 ₴ × 6) — 90,000 ₴

Total: 1,314,000 ₴

Stage 2 — Expansion (12 months):

Equipment (additional):

- VR headsets (3 pcs. × 25,000 ₴) — 75,000 ₴ (~$1,800)

- VR platform licenses (annual subscription) — 30,000 ₴ (~$700)

Software:

- Extended licenses for language trainers — 120,000 ₴ (~$2,850)

- Platform for speaking practice with native speakers (annual subscription) — 60,000 ₴ (~$1,430)

- Software for subtitling and audio description (annual) — 30,000 ₴ (~$700)

Educational materials:

- Purchase of textbooks (all languages) — 100,000 ₴ (~$2,380)

- Development of VR scenarios and interactive content — 80,000 ₴ (~$1,900)

Personnel (12 months):

- Payroll fund (expanded staff) — 2,628,000 ₴ (~$62,570)

Premises:

- Rent (12 months) — 240,000 ₴ (~$5,710)

- Utilities, internet (12 months) — 120,000 ₴ (~$2,850)

Exchange programs:

- Organizational expenses — 100,000 ₴ (~$2,380)

Contingency expenses (10%) — ~345,000 ₴ (~$8,210)

Total Stage 2: ≈ 3,798,000 ₴ (~$90,430)

Total cost of pilot launch and expansion (18 months):

Stage 1: ~3,156,000 ₴ (~$75,150)

Stage 2: ~3,798,000 ₴ (~$90,430)

Total Stages 1+2: ≈ 6,954,000 ₴ (~$165,580)

Stage 3 (scaling) will require a separate business plan after the model is tested in Chernivtsi.

Prepared by:

Tetyana Kryzhanovska

Director, PE “Language College Priority”