PSP “BUKOVYNA-FORALBERG”

Budget, calendar schedule, expenditure plan and profitability plan

for pilot planting of winter onion on 10–30 ha
within the Ukrainian-Korean Smart Village project

Orientation: the Korean market and onion processing for the ramyeon sector

Working document for presentation and preliminary negotiations

Calculation exchange rate: 1 USD = 42 UAH

Chernivtsi Oblast, Ukraine
2025

# 1. Proposed project topic

Topic: Pilot cultivation of winter onion on the lands of PSP “Bukovyna-Foralberg” for the Ukrainian-Korean Smart Village project, with further orientation toward the Korean market and onion processing for ramyeon production.

# 2. Brief essence of the project

PSP “Bukovyna-Foralberg” plans to use from 10 to 30 hectares of land from its own land fund for planting winter onion. The project is considered a pilot stage of Ukrainian-Korean Smart Village cooperation.

The main idea is to test the technology of growing winter-hardy onion in western Ukraine, with subsequent scaling to larger areas. In the short term, the project should produce a commercial result after the first season, and in the medium term it should become part of the production and logistics chain for storage, processing and export of products.

The strategic direction is the cultivation of onion that can be used for the Korean market, in particular for processing in the food industry and the ramyeon sector. This creates additional value for the project, because the products are oriented not only toward domestic sales but also toward contract cultivation for a specific buyer or processor.

# 3. Initial calculation conditions

| Indicator | Base value |
| --- | --- |
| Pilot area | 10–30 ha |
| Base cost model | $750,000 per 100 ha |
| Average cost per 1 ha | $7,500 / ha |
| Conversion rate | 1 USD = 42 UAH |
| Optimal soil pH for onion | 6.3–6.8 |
| Sales price range | $200–400 / ton |
| Main calculation scenario | 80 t/ha × $300/t |
| Pilot investment model | Korea: seeds + nutrients; Ukraine: field works and operating costs |
| Revenue distribution in Model A | Korea — 35%, local side — 65% |

# 4. Requirements for the land plot

For successful planting of winter onion, the land plot must have a suitable level of soil acidity — approximately pH 6.3–6.8. It is important to ensure a sufficient water supply, because onion requires active water supply during the period of bulb formation and thickening.

The plot must be well drained and contain enough organic matter. Before starting the project, it is necessary to check previous crops, residual herbicide effects, presence of weeds, the possibility of installing irrigation and availability of machinery.

The previous crop in the field must be harvested at least one month before winter onion sowing, so that plowing, soil preparation, fertilizer application and irrigation system setup can be completed.

# 5. General project budget depending on area

| Area | Budget, USD | Budget, UAH | Average cost per 1 ha |
| --- | --- | --- | --- |
| 10 ha | $75,000 | 3,150,000 UAH | $7,500 / ha |
| 20 ha | $150,000 | 6,300,000 UAH | $7,500 / ha |
| 30 ha | $225,000 | 9,450,000 UAH | $7,500 / ha |

For the main pilot scenario of 30 ha, the approximate full budget is $225,000, or about 9,450,000 UAH. This amount includes planting, crop care, irrigation, protection, fuel, labor, harvesting and maintenance of machinery.

# 6. Detailed expenditure plan

| Cost item | Per 100 ha | Per 10 ha | Per 20 ha | Per 30 ha |
| --- | --- | --- | --- | --- |
| Seeds | $220,000 | $22,000 | $44,000 | $66,000 |
| Nutrients / fertilizers, 3 applications | $90,000 | $9,000 | $18,000 | $27,000 |
| Base fertilizer NPK | $90,000 | $9,000 | $18,000 | $27,000 |
| Pesticides and plant protection | $100,000 | $10,000 | $20,000 | $30,000 |
| Water supply and irrigation equipment | $80,000 | $8,000 | $16,000 | $24,000 |
| Labor costs | $40,000 | $4,000 | $8,000 | $12,000 |
| Fuel | $40,000 | $4,000 | $8,000 | $12,000 |
| Harvesting materials | $40,000 | $4,000 | $8,000 | $12,000 |
| Lease and maintenance of agricultural machinery | $50,000 | $5,000 | $10,000 | $15,000 |
| Total | $750,000 | $75,000 | $150,000 | $225,000 |

## 6.1. Approximate investment distribution under Model A

| Area | Korean side: seeds + nutrients | Ukrainian side: field works and operating costs | Total budget |
| --- | --- | --- | --- |
| 10 ha | $31,000 / 1,302,000 UAH | $44,000 / 1,848,000 UAH | $75,000 / 3,150,000 UAH |
| 20 ha | $62,000 / 2,604,000 UAH | $88,000 / 3,696,000 UAH | $150,000 / 6,300,000 UAH |
| 30 ha | $93,000 / 3,906,000 UAH | $132,000 / 5,544,000 UAH | $225,000 / 9,450,000 UAH |

In this model, the Korean side provides highly resistant seeds and nutrients, while the Ukrainian side covers land preparation, fertilizer application, crop protection, irrigation, labor, fuel, harvesting and machinery.

# 7. Calendar implementation schedule

| Period | Works / decision | Responsible side |
| --- | --- | --- |
| By the end of June | Determination of the cultivation area: 10, 20 or 30 ha. Verification of water availability, machinery, agronomic support and previous crops. | PSP “Bukovyna-Foralberg” |
| June | First preliminary plowing to improve soil structure and destroy weeds. | Ukrainian side |
| Early July | Signing contracts for seeds and nutritional supplements with the Korean side. | Korea + Ukraine |
| Mid-July | Second preliminary plowing, irrigation system preparation, inspection of pumps, drip hoses or sprinklers. | Ukrainian side |
| Late July | Application of compost, base fertilizers, soil preparations, seed preparation. Transportation and customs clearance of seeds and nutritional supplements. | Korea + Ukraine |
| Mid — late August | Winter onion sowing. Holding a launch event / sowing ceremony for partners, investors and distributors. | PSP + partners |
| September — November | Seedling control, watering, weed control, first stage of field consulting. Inspection of crops in late October — early November. | Agronomists + Korean technologists |
| December — March | Wintering of the crop, monitoring of crop condition, control of freezing and damage risks. | PSP + technologists |
| Mid-March | First fertilization after winter. Invitation of distributors to inspect crops and start preliminary contracts. | PSP + Korean side |
| Mid-April | Second fertilization, control of above-ground growth, moisture management. | PSP + agronomists |
| May | Active water supply, weed control, preparation of machinery for harvesting. | Ukrainian side |
| Early — mid-June | Harvesting, sorting, preparation for sale or storage. | PSP + partners |
| By June 30 | Product sales, final settlements, analysis of pilot season results. | PSP + distributors |

# 8. Profitability plan

For the preliminary financial model, three scenarios were used: minimum, expected and maximum. The calculation is presented without taxes, long-term storage costs, processing, export logistics, certification and possible credit costs.

| Scenario | Yield | Price | Revenue per 1 ha | Profit per 1 ha after costs |
| --- | --- | --- | --- | --- |
| Minimum | 60 t/ha | $200/t | $12,000 | $4,500 |
| Expected | 80 t/ha | $300/t | $24,000 | $16,500 |
| Maximum | 120 t/ha | $300/t | $36,000 | $28,500 |

## 8.1. Profitability depending on area

| Area | Scenario | Revenue | Costs | Estimated profit | ROI to costs |
| --- | --- | --- | --- | --- | --- |
| 10 ha | Minimum | $120,000 | $75,000 | $45,000 | 60% |
| 10 ha | Expected | $240,000 | $75,000 | $165,000 | 220% |
| 10 ha | Maximum | $360,000 | $75,000 | $285,000 | 380% |
| 20 ha | Minimum | $240,000 | $150,000 | $90,000 | 60% |
| 20 ha | Expected | $480,000 | $150,000 | $330,000 | 220% |
| 20 ha | Maximum | $720,000 | $150,000 | $570,000 | 380% |
| 30 ha | Minimum | $360,000 | $225,000 | $135,000 | 60% |
| 30 ha | Expected | $720,000 | $225,000 | $495,000 | 220% |
| 30 ha | Maximum | $1,080,000 | $225,000 | $855,000 | 380% |

## 8.2. Main scenario for 30 ha

• Area: 30 ha.

• Total costs: $225,000 or approximately 9,450,000 UAH.

• Expected yield: 80 t/ha.

• Expected sales price: $300/t.

• Expected revenue: 30 ha × 80 t/ha × $300/t = $720,000.

• Estimated profit after field costs: $495,000.

• Estimated profitability to direct costs: about 220%.

## 8.3. Profit distribution under the 35% / 65% model for 30 ha

| Scenario | Total profit | Korea share 35% | Local side share 65% | Estimated ROI of Korean side | Estimated ROI of local side |
| --- | --- | --- | --- | --- | --- |
| Minimum | $135,000 | $47,250 | $87,750 | 51% | 66% |
| Expected | $495,000 | $173,250 | $321,750 | 186% | 244% |
| Maximum | $855,000 | $299,250 | $555,750 | 322% | 421% |

# 9. Financing plan and expenditure flow for 30 ha

| Period | Main costs | Approximate amount, USD | Comment |
| --- | --- | --- | --- |
| June | Preliminary plowing, plot assessment, machinery preparation | $12,000 | Initial field works and technical preparation |
| July | Seeds, nutrients, base fertilizers, irrigation, protection | $144,000 | Largest budget load, including imported components |
| August | Sowing, fuel, labor, machinery, initial agronomic works | $27,000 | Key month of crop establishment |
| September — November | Care, watering, weed control, consulting | $12,000 | Support for normal crop entry into winter |
| March — May | Fertilization, water, care, preparation for harvest | $18,000 | Active spring growth management |
| June | Harvesting, harvesting materials, machinery, shipment | $12,000 | Final operational phase |
| Total | Full budget for 30 ha | $225,000 | Approximate cost model |

# 10. Sales plan and market logic

At the first stage, products may be sold on the domestic market of Ukraine or through preliminary arrangements with distributors. In March, after successful wintering, it is advisable to organize crop inspections for potential buyers and conclude preliminary contracts.

Strategically, the project is oriented toward the Korean market and the possibility of contract cultivation of onion for the needs of the food industry. A separate direction is the use of onion as raw material for the ramyeon sector, where stability of quality, volume and supply is important.

In the future, the project may be connected with a future fruit and vegetable warehouse / agro-hub that will provide storage, sorting, packaging, processing and export logistics.

# 11. Main risks and mitigation measures

| Risk | Impact | Mitigation measures |
| --- | --- | --- |
| Insufficient water supply | Lower yield and bulb quality | Preliminary verification of water sources, installation of drip or combined irrigation |
| Residual herbicide effect after previous crops | Problems with germination and plant development | Analysis of field history, agrochemical testing, avoidance of plots after crops treated with strong herbicides |
| Strong winter winds or freezing | Crop damage during wintering | Selection of plots without excessive wind load, use of frost-resistant seeds |
| Sales price fluctuation | Reduced profitability | Preliminary contracts with buyers, sales diversification: Ukraine, EU, Korean direction |
| Lack of machinery during peak periods | Delay in sowing or harvesting | Advance reservation of machinery, lease and service contracts |
| Logistics and customs delays for seeds | Shift of the sowing calendar | Early contract execution, planning of air delivery, time reserve until the end of July |

# 12. Development strategy

| Stage | Period | Content |
| --- | --- | --- |
| Pilot | 2025–2026 | Planting 10–30 ha on the lands of PSP “Bukovyna-Foralberg”, technology testing, yield assessment, formation of first contracts. |
| Scaling | 2026–2028 | Expansion of areas to 100–500 ha through partner farms, mechanization, formation of a farmers’ association, attraction of ODA, EDCF, EBRD. |
| Cluster | 2028+ | Creation of a winter onion cluster: seeds, fertilizers, agricultural materials, storage, processing, export, food industry. |

# 13. Conclusion

The pilot project of PSP “Bukovyna-Foralberg” on an area of 10–30 ha is financially feasible for the first stage of Ukrainian-Korean Smart Village cooperation. The most indicative scenario is 30 ha, where the full budget is about $225,000, and the expected profit at a base yield of 80 t/ha and a price of $300/t may amount to approximately $495,000.

The project has high strategic value, because it combines field production, Korean agrotechnologies, the prospect of contract cultivation and the possibility of further integration into a fruit and vegetable warehouse, processing and export logistics.

The recommended next step is to conduct agrochemical testing of specific plots, determine the final pilot area, confirm the water source, fix the investment model with the Korean side and prepare a contract for seeds, nutrients and technological support.

# 14. Short financial note for presentation

| Indicator | 10 ha | 20 ha | 30 ha |
| --- | --- | --- | --- |
| Total budget | $75,000 | $150,000 | $225,000 |
| Budget in UAH | 3,150,000 UAH | 6,300,000 UAH | 9,450,000 UAH |
| Expected revenue | $240,000 | $480,000 | $720,000 |
| Expected profit | $165,000 | $330,000 | $495,000 |
| Local investment under Model A | $44,000 | $88,000 | $132,000 |
| Korean investment under Model A | $31,000 | $62,000 | $93,000 |

Note. The calculations are preliminary and intended for presentation, negotiations and preparation of a working financial model. Actual indicators depend on land quality, water supply, weather, purchase prices, logistics, taxes, exchange rate, costs of storage and processing, and contract terms with buyers.